Worldwide Forgiveness Alliance

Business Plan  - Draft

Working Document

As of:  Aug 27, 2001

Mission:  Promoting the awareness and practice of forgiveness

Planning Group on Aug 27, 2001:

- Robert Plath

- Noel McInnis

- Fred Luskin

- Danielle Gallisa

- Judy Trummer

- Emmie Tse

Objectives:

| 2001 Objectives: | Metrics | Target Completion Date |
| --- | --- | --- |
| Honor heroes of forgiveness | Honor 4 Heroes in SF, USA. | Aug 5, 2001-cmpleted |
| International Forgiveness Day Event in SF | Event had over 500 participants | Aug 5, 2001 – completed |
| International Forgiveness Holiday – First Global International Holiday | Establish commitments from xx # of cities to replicate Forgivness Day Event | Dec 31, 2001 |
| Increase Membership in the US, EMEA, Asia-Pacific, Canada, Americas outside US | US from xxx beg of yr to xxx by end of yr | Dec 31, 2001 |
| Develop Strategic Alliances with other organizations with similar mission that may include the following: - Dr. Fred Luskin, Director of Stanford Forgiveness Research - Pioneers of Forgiveness - Season of Non-Violence - A Campaign for Forgiveness Research (www.forgiving.org) - Archbishop Desmond Tutu: Co-chair - Dr. Robert Coles: Pulitzer Prize winning author, Co-chair - Ruby Bridges Hall: community activist - Jimmy Carter: Endorser and Former President - Dr. Everett Worthington: Executive Director | Agreed on joint campaign, program with other organizations | Dec 31, 2001 |
| Develop Plan for Fundraising | Tbd | Tbd |
| Develop Train the Trainer Program | Tbd | tbd |
| Develop template for other cities to replicate the SF Forgiveness Day Event | tbd |  |
| Design Strategic Board of Directors with specific skillsets that would strengthen the organization: - Membership - Marketing - Events Planning - Internet Marketing - Internet Technologist - Fund Raising - Etc.. | Tbd | t |
| Completed Event Program Development - Season of Non-Violence – awarding civil rights heroes of forgiveness | Tbd |  |
| Develop Internet Community Strategy & Program | Tbd |  |
| Develop membership communication program | Tbd |  |
| Develop communication program for key members and Board of Directors. | Tbd |  |

Strategy include specific action plans and resources required: