Timeline

Workshop Timeline:

Every workshop will follow approximately this time line:

Begin:

Shaping: What’s working and what do you need help with?

Commitments Debrief their commitments - -Keep it brief.

Commitments to the workshop (i.e. data collection, Business Analysis, cell phone etc.

Material to be presented

Commitments for next session

End

Coaching Timeline:  (yellow = Coaching session an DVD)

| Wk | Coaching For Agents | Recruiting For Managers | Need on DVD |
| --- | --- | --- | --- |
| -1 | Invitations go out to the appropriate agents for Transaction Group | Install and learn Real Data Strategies database system, Collect the agents appropriate for recruiting | Trainer: Instructions in Work Book |
| 0 | Orientation – 1½ - 2 hours (On DVD) Interactive with Manager and DVD Who wants to commit? Make appointments with the ones who say yes. Invite them to second interview. | Phone Call to Coach Have meetings with candidates. Select the group. (More than # needed.) Go over the needed commitments to time. Do RDS data for selected agents | Trainer: Either use the DVD or do it live. Orientation on DVD for use by Manager. |
| 1 | Coaching Workshop 1 – 1 to 2 hrs Commitment to coaching series. Everyone commits to the timeline. Foundation for group Hand out Business Analysis Commitments to collecting the data | Phone Call to coach Have prepared Business Analysis sheets for Selected Agents to be used at SELL with their permission | Trainer instructions on foundation. Agent: Foundation License This is Your Training |
| 2 | SELL I and II Hold Agents accountable for supplying data on Transactions. | Attends SELL Meeting with QMS Coach. Recruiting scripts Practice Review doing Business Analysis for recruiting. |  |
| 3 | SELL III Sample Business Analysis for 2-3 people at training Demo #/Source, income/Source, Volume/Source | Attends SELL Meeting with Trainer Starts Making Coffee meetings with Trainer |  |

| 4 | Coaching Workshop 2 – 2 hours Manager does analysis on people who were not done at SELL Get commitment to collect SOI/Past Clients/leads names, email, address, phone, etc data Commitments to the Time management learned in SELL. | Phone call to coach re recruiting calls made. Review using RDS data and Business Analysis for recruiting. | Trainer: instructions on doing the Analysis What the Analysis means Agents: What it means to you What to look for. Excel spreadsheets |
| --- | --- | --- | --- |
| 5 | Scientific Marketing Use the Business Analysis data generated | Meeting with Trainer Debrief Coffee meetings Look over Business Analysis for recruiting for prospects. Review scripts. |  |
| 6 | Coaching Workshop 3 – 2 hours Generate Business Plan for each person. Based on Scientific marketing and Business analysis. Get commitment to bring client information, including contact and address. | Phone call to coach | Trainer: instructions How to generate the business plan. How to ask for the right commitments Agents: Review the protocols for Jelly Bean Jar Introduce IMS system |
| 7 | Coaching Workshop 4 – 2 hours Making Data Meaningful Get the data into a format so that it can be sent, contacted, etc. Introduce Impact Marketing function…Website Commitment to data in place by next session. Bring cell phone and data to next session. | Phone Call to coach | Trainer: Using IMS Agents: Review of Scientific Marketing principles for Veterans. |
| 8 | Coaching Workshop 5 – 2 hours Scripts Practice and memorization Schedule a call night. Get Commitments to attendance. Review of S. M.: Red vs Green, protocols, using it in Business Plan. Commitment to a number of calls to Jelly Bean Jar for permission. -Or (if not enough JB) Add 10 to JBJ /call what there is. Commitments to BP actions. | Phone call to coach | Trainer: Further review of Scientific Marketing for use by veterans What kinds of commitments you are looking for. Agents: Further review |
| 9 | Coaching Workshop 6 – 1 hours Accountability for calls made and JB added Pin Analysis for past weeks | Phone call to coach | Trainer: Review accountability language Agents: Review PIN Prioritizing vs. AND thinking. |
| 11 | Committing Communications™ Probing/Consultation Training (3 days) | Meet with coach |  |
| 12 | Coaching Workshop 7 - 1 hour Wrap up Discussion about changes Team up with partner. | Phone call to coach | Trainer: creating closure, wrap up, inspiration. Partnerships in accountability Get referrals to OB agents for office |