Conference Production

Piecing Together

a Better World

| # Project Name | Piecing Together a Better World |
| --- | --- |
| # Vision | Increase public awareness of and participation in practices, projects, and programs of collaborative, non-adversarial advocacy on behalf of well-being (personal, social and economic), peace, and environmental integrity. - Establish a socio-evolutionary context - Feature successful demonstrations - Facilitate greater interconnectivity among practitioners. |
| # Objectives | # 1. Produce a successful, one-day conference for 2,000+ persons on the power and practice of collaborative, non-adversarial advocacy. # 2. Acquaint participants with the nature of collaborative, non-adversarial advocacy and the necessity of such advocacy for effective advancement of well-being, peace, and environmental integrity. # 3. Feature actual practices, projects, and programs of collaborative, non-adversarial advocacy, in which participants can be involved. # 4. Conclude conference with small-group dialogue groups for participants’ sharing of what they have been inspired to do individually, and of what they envision being collectively achievable via post-conference networking and further programming. |
| # Success Criteria | - Create participant “buy-in” to collaborative, non-adversarial advocacy. - Facilitate participant involvement in several practices, projects and programs of collaborative, non-adversarial advocacy. - Inspire new initiatives of collaborative, non-adversarial advocacy. - 90% overall satisfaction rating. - 90% active participation rate. |
| # Project Deliverables | # Instructive, entertaining, and exciting one-day conference. # Eight or more opportunities for involvement in practices, projects, and programs. |
| # Sponsor | Global Brain Empowerment Network |
| # Focalizing Team # Project Team Organization | Solara Amour, Gabrielle and Thomas Chavez, Noel McInnis Core Project Team: - Noel McInnis, Project Director, Webmaster, Overview-Enrollment-Program Coordinator - Gabrielle Chavez, Consciousness Focalizer - Jay Brandon, Corporate Funding - __________, Volunteer Coordinator - __________, Publicity - __________, Database management - __________, Bookkeeping - Hiedi Simon, Event Manager - John Larson, Food Manager - Gabrielle Chavez, Conference Moderator - __________, Set-up/clean-up coordinator - __________, Hospitality (consultants) - __________, Registration/information table - __________, Exhibits manager |