Conference Production

Piecing Together

a Better World

| # Project Name | Piecing Together a Better World |
| --- | --- |
| # Vision | Increase public awareness of and participation in practices, projects, and programs of collaborative, non-adversarial advocacy on behalf of well-being (personal, social and economic), peace, and environmental integrity. - Establish a socio-evolutionary context - Feature successful demonstrations - Facilitate greater interconnectivity among practitioners. |
| # Objectives | # 1. Produce a successful, one-day conference for 2,000+ persons on the power and practice of collaborative, non-adversarial advocacy. # 2. Acquaint participants with the nature of collaborative, non-adversarial advocacy and the necessity of such advocacy for effective advancement of well-being, peace, and environmental integrity. # 3. Feature actual practices, projects, and programs of collaborative, non-adversarial advocacy, in which participants can be involved. # 4. Conclude conference with small-group dialogue groups for participants’ sharing of what they have been inspired to do individually, and of what they envision being collectively achievable via post-conference networking and further programming. |
| # Success Criteria | - Create participant “buy-in” to collaborative, non-adversarial advocacy. - Facilitate participant involvement in several practices, projects and programs of collaborative, non-adversarial advocacy. - Inspire new initiatives of collaborative, non-adversarial advocacy. - 90% overall satisfaction rating. - 90% active participation rate. |
| # Project Deliverables | # Instructive, entertaining, and exciting one-day conference. # Eight or more opportunities for involvement in practices, projects, and programs. |
| # Sponsor | Global Brain Empowerment Network |
| # Focalizing Team # Project Team Organization | Solara Amour, Gabrielle and Thomas Chavez, Noel McInnis Core Project Team: - Noel McInnis, Project Director, Webmaster, Briefing-Enrollment-Program Coordinator - Gabrielle Chavez, Consciousness Focalizer - Jay Brandon, Corporate Funding - __________, Volunteer Coordinator - __________, Publicity - __________, Database management - __________, Bookkeeping - Heidi Simon, Event Manager - John Larson, Food Manager - Gabrielle Chavez, Conference Moderator - __________, Set-up/clean-up coordinator - __________, Hospitality (consultants) - __________, Registration/information table - __________, Exhibits manager |
| - Core Team Responsibilities | Sponsor: # Provides resources for project core team - Helps define project requirements - Reviews and approves project plans and budget - Keeps team interfaces in balance – resolves cross-functional roles and task issues - Executive Champion for project: - Visible and on-going support - Escalation point to Steering Committee - Maintains upper management awareness of project value and milestone completions Project Manager: - Initial planning & scheduling - Project performance analysis - Monitoring & control of project processes - Organization & personnel planning - Customer relationship management - Maintaining the technical/business interface - Project mentor and expert for sub-teams - Escalation point for project issues - Provides 1:1 time for Project Leads Communication Team: - Determine Theme - Develop Curriculum Sizzle - Communicate Logistics |
| # Core Team Responsibilities cont’d | Curriculum Team: - Identify training needs - Prioritize and select core curriculum - Develop Symposium Agenda - Identify sub-teams for curriculum development and/or Vendor selection - Complete Vendor contracts (partner with logistics team) - Build course descriptions and outlines - Develop curriculum or partner with Vendor to customize curriculum - Run beta sessions - Identify Speakers/Trainers for all sessions - Train the trainer for internal speakers - Develop tracks for core roles - Prep key note speakers - Develop team building exercise Logistics Team: - Monitor and manage budget - Complete Site selection - Purchase Collateral – Partner with Communication Team - Determine and order Menu - Determine and order Decor - Manage Multi-media for event - Determine Symposium flow and timing from agenda - Build and manage Registration site - Awards Banquet logistics/décor – partner with Colette French - Manage timeline and due dates - Order material: Notebooks, handouts, agenda, sign-in sheets - Determine room arrangements and room coordinators - Determine on-site registration process and manage - Manage speaker check-in - Determine and communicate travel recommendations for the field |
| # Project Team Members assigned to each of the three project areas | - Provide realistic task/deliverable estimates - Complete assignments per requirements/timelines - Inform Project Lead of task status on a regular/agreed upon basis - Bring risks, issues, impacts to Project Lead for resolution - Share relevant information in timely manner - Be a team player |
| # Project Communication Plan | - January – March, 2202: - Core Team Bi-weekly project meeting, Sharon Decker attending – Agenda Template provided - Team Leads Bi-weekly status report – template provided - April – July 2002 - Weekly project meeting, Sharon Decker attending until Tracy Kellum returns mid-June - Team Leads Weekly status report - Real time communication of urgent issues escalated to Tracy and Sharon for approval and resolution - Regularly scheduled project updates to Steering Committee and project team - Team Leads determine regularity and scope of sub-team meetings, status check-in, communication and milestone management |
| # High Level Project Timeline # Assumptions, Dependencies, Exclusions | See Project Timeline document provided Assumptions: - Project will stay within budget and be completed the week prior to the event. - Staffing professionals and recruiters will be available to act as project team members and SME’s on the 3 project areas - Project team will deliver on time, stay engaged - Quality is built into our approach and processes Dependencies: - Schedules/Timeline of work completion later in project - Each sub-team depends on others to complete final deliverables |

Project Management Processes

## Scope/Change Mgmt – create change request process

## Issue Resolution – maintain overall project issue log

## Issue Log is part of project meeting agenda template:

## Add new issues and assign owner

## Review status of current issue

## Resolve and close issue/s at each project meeting

## Each Team Lead to maintain their own issue log as needed

## Risks:  Identify risks on project

## Schedule:  Managed by Logistics Team Lead

## Budget: Managed by Logistics Team Lead

## External Communication Plan Managed by Communication Team Lead

## Internal Communication Plan:

- Identify how the Project Team Members and Steering Committee receive updates about the project

  - Regular project meetings

  - Email (official, ad-hoc)

  - Phone calls

## Escalation:

## Identify triggers – impact to scope, schedule, and budget

# Establish escalation process – when, how and who to escalate!

2002 Staffing Symposium Timeline

| December | - Target Dates - Budget - Determine Scope and Expectations - Taskforces Formed - Commit to location |
| --- | --- |
| January | - Conduct Training Needs Assessment - Taskforce meetings begin - Determine Theme - Communicate dates – create hype - Identify Training needs - Prioritize Curriculum |
| February | - Vendor Search - Curriculum sub-teams form |
| March | - Course Outlines due - Vendor selection complete - Core participant tracks determined |
| April | - Vendor Contracts complete - Course description and sizzle complete - Select and order give-aways - Order notebooks |
| May | - Agenda Complete - Curriculum complete - Registration site built - All Speakers confirmed |
| June | - Registration - Beta Sessions - Decorations determined and ordered - Awards Dinner - FY02 Prepays due - Train the trainer session for speakers |
| July | - Registration closed and scrubbed - Train the trainer sessions complete - Beta Sessions complete - Materials ordered - AV needs determined and ordered - Menu determined and ordered - Room requirements determined - Assign rooms and coordinators |
| August | - Conduct Symposium - Survey - Post Mortem |