INDEPENDENT CONTRACTOR’S AGREEMENT

TO:		Noel McInnis/Global Brain Empowerment Network

FROM:	Hiedi Simon

DATE:		February 11, 2005

The following will outline our agreement and summarize the terms of our proposed arrangement.  If you are in agreement with the terms, please sign below and return to the contract to me at: 30825 SW Kensington Drive, Wilsonville, OR 97070.

The Global Brain Empowerment Network (GBEN) has agreed to retain me, Hiedi Simon, as an independent contactor beginning February 14, 2005.   I will step in as the Event Manager for the conference taking place September 23 – 25, 2005.

In this role, I will:

- Be available via phone and/or email to consult on the event.

- Attend one 4 hour planning meeting per month up until the event.

- Coordinate event details such as: site set up, clean up, audio/visual requirements, etc.

  - Be the liaison between GBEN and the Oregon Convention Center.

  - Monitor the lead volunteers to support their progress and develop a relationship that will serve the highest good for the conference.

- Be available for up to 20 hours the week prior to the event to support last minute planning and preparation.

- Work the entire event as the manager of conference logistics and coordination.

  - Make sure the event plan is followed and troubleshoot as necessary.

These services shall be provided for a total fee of $4,000.00.  Payment will be split into 4 equal installments of $1,000.00 due as follows:

1st installment: 	due immediately along with the signed agreement

2nd installment:	due May 19, 2005

3rd installment:	due July 19, 2005

4th installment:	due September 19, 2005 (one week prior to the event)

Any additional hours to be billed will be agreed upon by both parties and will be paid at the rate of $50.00 per hour.  In addition, all business long-distance phone calls, faxes, copies, reimbursable materials and travel expenses will be added to the next appropriate payment.  This contract shall be valid for until September 26, 2005.

As an independent contractor, I understand that I am not authorized to sign contracts or bind GBEN in any manner without express permission from GBEN directly.

GBEN will not deduct or withhold any taxes, FICA or other deductions and, as an independent contractor, I will not be entitled to any fringe benefits such as unemployment insurance, medical insurance or other such benefits, which may be offered to regular employees.

During this time, I may be in contact with or directly working with proprietary information that is important to GBEN and its competitive position.  Examples of such proprietary information are product design or content, logos, trade name, production technique or process, pricing or sales and marketing plans that are not generally known by the public or by competitors of GBEN.  There may be other information that is proprietary and such information must be kept confidential and may not be used at any time or in any manner other than as expressly authorized by GBEN, in connection with the work I do for the organization.  When I complete this contract, all materials, which contain such proprietary information will be returned.

By accepting this contract, I agree that all design, copyrightable work and other creative work, prepared or originated by me for GBEN, or during or within the scope of my work for GBEN, constitute work made for hire, all rights to which are owned by the organization.  I hereby assign all copyrights and other rights, title, and interest, including patent rights, trade secret rights, trademark rights, and all other intellectual property rights, in all such work to the Global Brain Empowerment Network.

Either party upon thirty (30) days written notice can terminate this contract.

By:

Hiedi Simon					Social Security No. or Federal ID #:

Successful Creations

I AGREE TO THE ABOVE TERMS:		Date:

________________________________

Noel McInnis

Global Brain Empowerment Conference