MILESTONES

The Road to There (August 6) From Here

ACTIVITY							DATE ACCOMPLISHED

Structure joint venture					A.S.A.P. (completion date needed)

Fund solicitation letters					A.S.A.P. (completion date needed)

Update website						Continuous

Initiate Pioneers of Forgiveness (POF)				May 1

Obtain commitments from speakers and award recipients	Prior to May 10

Print brochures for IFD and POF				May 10

Mailings to mayors & churches (includes brochures)		Mid-May (more exact date needed)

Follow-up to mailing to mayors and churches			Start a week after mailings (continuous)

Commence e-mail networking					Mid-May (continuous until event)

Mail press kits and sent					Mid-June (more exact date needed)

Place webcast order with 3rd party vendor			June 16

Finalize location						July 1

Place ads							July 15+

Prepare event’s volunteer support team			Late July – August 6

Webcast team set up at location				Morning of August 6

DO IT!!								August 6